## Slide 1: Spark NZ Residential fibre fault resolution
Decision requested: NZ$36,846 excluding GST
Ryan Li · ali409 · INFOSYS 704 A2-D2
Six-week diagnosis for an investment decision
Spark NZ · Individual operational business case
Proposed engagement · September 2026
Notes: SPOKEN SCRIPT — 01 — 20 seconds
Hello, I’m Ryan Li. I propose a six-week diagnosis of Spark’s residential fibre faults, to identify the cause and decide whether further investment is worthwhile.
EVIDENCE AND QUALIFICATIONS
The diagnostic outputs will test the proposed causes and compare affordable options, including a smaller change using existing tools. The value of this information has not been monetised. Approval depends on the sponsor judging the outputs useful enough to justify their cost. The subsequent NZ$117,162 is uncommitted budget, not an achieved saving.
核心请求是购买六周内可核验的诊断产出：服务基线、带成本的方案比较和下一步投资建议。NZ$36,846 不含 GST，是诊断阶段上限。诊断信息的价值尚未货币化，是否值得购买取决于赞助人判断；不能把后续未承诺预算称为已实现节约。
SOURCES
Author proposal, planning assumption or reconstructed process. Not an observed Spark result.

## Slide 2: Spark’s service context
FY26 broadband revenue
−4.8%
Broadband connections
+42 interaction NPS
Consumer and SME
Up 2 points year on year
NZ$596m
Total broadband figures are not a residential fibre fault baseline.
Spark New Zealand, 2026b, p. 16; Spark New Zealand, 2026a, p. 21
Operational focus
Locate avoidable waiting and repeat work
in residential fibre fault handling.
Notes: SPOKEN SCRIPT — 02 — 20 seconds
Spark’s broadband connections fell while customer interaction scores improved. These mixed signals justify checking service performance, but do not show that fault handling caused customer losses.
EVIDENCE AND QUALIFICATIONS
用混合的业务背景保持客观。596m 和 −4.8% 是整体 broadband；+42 是 Consumer/SME interaction NPS，不能说成 42% 满意度，也不能认定客户流失由故障处理导致。
SOURCES
Spark New Zealand Limited. (2026b). Spark New Zealand FY26 results summary.
https://investors.sparknz.co.nz/FormBuilder/_Resource/_module/gXbeer80tkeL4nEaF-kwFA/doc/H2FY26_Results_Presentation.pdf
Spark New Zealand Limited. (2026a, August 20). Spark annual report FY26.
https://investors.sparknz.co.nz/FormBuilder/_Resource/_module/gXbeer80tkeL4nEaF-kwFA/doc/FY26_Annual_Report.pdf

## Slide 3: Customer feedback warrants investigation
Satisfaction with issue handling
Chart: 
| Resolution speed | Staff knowledge
Top-two satisfaction | 0.36 | 0.46
Mobile + Broadband
Spark sample: n = 795
July 2025 to June 2026
Top-two responses (4 or 5 out of 5). Customer perceptions, not restoration rates.
Commerce Commission, 2026b, p. 1; Commerce Commission, 2026a, pp. 2, 4
Notes: SPOKEN SCRIPT — 03 — 20 seconds
These survey results combine mobile and broadband customers. They highlight concerns about issue handling, but do not measure residential fibre restoration or establish its causes.
EVIDENCE AND QUALIFICATIONS
36% 和 46% 都是对问题处理的满意度，各题 Spark 样本均为 n=795，混合 mobile/broadband。它们不能代替内部光纤流程基线，不能与较早不同样本的数据直接比较。
SOURCES
Commerce Commission. (2026b). Customer service and billing rankings – June 2026.
https://www.comcom.govt.nz/assets/Uploads/Customer-Service-and-Billing-Rankings-June-2026.pdf
Commerce Commission. (2026a, August 18). Consumer satisfaction metrics: Methodology & guide – June 2026.
https://www.comcom.govt.nz/assets/Uploads/Consumer-Satisfaction-Metrics-Methodology-Guide-June-2026.pdf

## Slide 4: A bounded operational problem
Start
Residential fibre fault contact
Finish
Verified stable restoration
Outside scope
Billing, installations, plan changes,
mobile, wireless broadband
and enterprise services.
Agree region and partner
with Spark at initiation.
One region and one principal partner
Proposed scope. Technical retest plus customer confirmation where obtainable.
Include unresolved and reopened episodes.
Notes: SPOKEN SCRIPT — 04 — 20 seconds
The scope follows residential fibre faults from first contact to stable recovery, within one region and one principal partner. Spark must first agree how recovery is measured.
EVIDENCE AND QUALIFICATIONS
边界为住宅光纤故障首次联系至稳定恢复。单一区域、单一主要技术合作方都尚待客户选择，不能写成已选 Chorus 或 Nokia。恢复定义必须同时用于试点与对照。
SOURCES
Author proposal, planning assumption or reconstructed process. Not an observed Spark result.

## Slide 5: AS-IS handoff requiring validation
Referral sent
What happens in between?
Who owns the waiting case?
When does the partner accept?
When is escalation needed?
Episode checks: referral time, acceptance, owner and escalation.
Author reconstruction in SAP Signavio. Handoff delay remains a hypothesis.
SAP, n.d., Modeling with the Editor
Notes: SPOKEN SCRIPT — 05 — 20 seconds
The referral reaches a partner, but the waiting period needs investigation. Case records must show who owns the case, when acceptance occurs and whether escalation works.
EVIDENCE AND QUALIFICATIONS
展示现有 Signavio AS-IS 交接局部。它是作者重建、等待验证的模型，并不能证明 Spark 真的没有责任人或接收机制。观察重点是两个事件之间的等待与责任。
SOURCES
SAP. (n.d.). Modeling with the editor. Managing Business Processes with SAP Signavio Solutions, Unit 4, Lesson 3.
https://learning.sap.com/courses/managing-business-processes-with-sap-signavio-solutions/the-editor-quick-n-easy-modeling_fd121490-31f9-4229-a10a-8a3a68972fa3

## Slide 6: Competing causes and candidate responses
Evidence determines the intervention
Cause to investigate | Candidate response
Missing case context | Locate the gap before choosing a control
Diagnosis or routing | Improve first diagnosis and routing
Handoff ownership | Named owner and explicit acceptance
Communication | Improve existing customer updates
P2: integration for evidenced status gaps. P4: minimum combination. P5: separate structural-change approval.
Rosenbaum et al., 2017, pp. 143–150
Method: MECE issue tree and customer journey mapping
Test competing causes before selecting P1–P6.
Notes: SPOKEN SCRIPT — 06 — 20 seconds
I would test all four explanations before selecting a response. Customer journey mapping links them to customer effort. Evidence may support a small change or stopping.
EVIDENCE AND QUALIFICATIONS
A stage-based MECE issue tree structures H1 context reconstruction, H2 diagnosis or routing, H3 handoff ownership and H4 communication. Customer journey mapping follows Rosenbaum et al. (2017). Candidate links are H2 to P6 routing, H3 to P1 ownership and H4 to P3 communication. H1 first requires locating the missing context. P2 is considered where responsibilities work but missing or delayed partner status creates avoidable work. P4 combines only necessary evidenced measures. P5 structural change needs separate authority. These are competing explanations, not confirmed causes.
H3 不是已确认根因。H1 不与 P2 固定对应；先定位缺失的上下文。P2 适用于责任已清楚、但合作方状态缺失或延迟造成额外工作的情形。用阶段式 MECE issue tree 与 customer journey mapping 组织分析。P4 只组合有证据必要的措施，P5 需要独立授权。
SOURCES
Rosenbaum, M. S., Otalora, M. L., & Ramírez, G. C. (2017). How to create a realistic customer journey map. Business Horizons, 60(1), 143–150.
https://doi.org/10.1016/j.bushor.2016.09.010

## Slide 7: Success means verified service improvement
Targets apply only when diagnosis supports the cause
Outcome | Proposed target
Restoration time | 15% lower median if ownership is causal
Longer waits | No worsening at the 90th percentile
Recontacts per eligible episode | 15% fewer if communication is causal
Correct first routing | +10 percentage points if routing is causal
Partner acceptance time | Agree target with baseline and partner
Adjusted comparison cohort. Retain unresolved outcomes and monitor seven-day reopenings.
Stable restoration requires a technical retest
and customer confirmation where obtainable.
Notes: SPOKEN SCRIPT — 07 — 20 seconds
If evidence supports ownership delays, target fifteen percent lower median restoration time, without worsening the ninetieth percentile. Compare similar cases and retain unresolved outcomes.
EVIDENCE AND QUALIFICATIONS
K1: elapsed hours from the earliest recorded fault or contact to stable restoration, reported as median and P90. Report unknown onset and incomplete episodes separately. Stable restoration requires a successful technical retest plus customer confirmation where obtainable; the service owner agrees this rule in week 2. K2: recontacts per eligible episode, with a 15% reduction conditional on H4. K3: correctly routed first-time episodes divided by episodes with reviewed routing and cause; report unknown classifications. The conditional H2 target is +10 percentage points. K4: elapsed hours from referral sent to explicit acceptance by a named receiving owner, reporting median/P90 and missing or pending acceptance. Set its numerical target at G1 with the baseline and partner, and test whether reduced acceptance delay mediates K1 improvement. Use a concurrent comparable queue or feasible staggered rollout, adjusting for case mix and seasonality. Retain unreachable, unresolved and reopened cases. Insufficient follow-up supports feasibility conclusions only. Proposed timely-update target: 90% if H4 is supported. Investigate a rise in seven-day reopenings above 2 percentage points.
主要口述目标为：若责任交接原因得到支持，恢复时长中位数相对可比队列缩短 15%，同时 P90 不恶化。P90 指第 90 百分位，不等于所有最长等待。重复联系减少 15% 依赖 H4；首次正确分流提升 10 个百分点依赖 H2。接受时长从发出 referral 到具名接收人明确接受，数值目标待 G1 同意。完整操作定义在英文备查说明及 PPT 备注；不能以关闭工单代替真正恢复。
SOURCES
Author proposal, planning assumption or reconstructed process. Not an observed Spark result.

## Slide 8: What Spark receives after six weeks
Agreed scope and
service definitions
Baseline and evidence
for competing causes
Costed options and
a funding recommendation
Weeks 1–2
Weeks 2–4
Weeks 5–6
Evidence for a revised scope or a decision to stop
G1: supported mechanism and affordable design, or stop. Proposed record-readiness threshold: ≥90%.
Approved data request
Common restoration rule
Recent 8–12 week sample
Completed and unresolved cases
Case reviews and staff interviews
Revised costs and options
Feasible pilot sample
Notes: SPOKEN SCRIPT — 08 — 20 seconds
By week six, we aim to deliver a baseline, evidence and costed options. The sponsor can then approve an affordable design, change scope or stop.
EVIDENCE AND QUALIFICATIONS
Diagnosis uses deidentified episodes from the latest 8–12 weeks, including completed and unresolved cases. Deliverables are D1 scope, eligible episodes, access owners and approved data request; D2 event dictionary, extraction and approved common restoration rule; D3 walkthroughs, staff interviews and evidence for and against H1–H4; D4 comparison of P1–P6, sample feasibility and revised costs. G1 approves a supported mechanism and affordable design, changes the candidate/scope, or stops. Ryan presents evidence; Rae checks value, Francis strategic fit and Xuan adoption. Discovery does not itself provide a powered causal estimate. Determine pilot sample size using baseline variation and clustering.
第六周交付明确的决定依据：服务定义与基线、支持和反对各原因的证据、P1–P6 比较、样本可行性和修订成本。G1 选择有证据且可负担的设计、调整范围或停止。诊断用近期 8–12 周去标识记录，包含已完成与未完成案例；不保证六周诊断就能得到有统计检验效力的因果结果。
SOURCES
Author proposal, planning assumption or reconstructed process. Not an observed Spark result.

## Slide 9: Conditional P1 and the intended service benefit
Named acceptance if handoff ownership is causal
Visible responsibility
Less waiting and chasing
Faster recovery
Fewer customer follow-ups
P1 controls: named acceptance, referral clarification and escalation.
Test service benefits and total handling effort. Retain unresolved outcomes.
Any later simulation needs validated time, volume, resource and cost inputs.
SAP, n.d., Modeling with the Editor; SAP, n.d., Performing Simulations
Notes: SPOKEN SCRIPT — 09 — 20 seconds
If ownership contributes to delays, named acceptance and escalation could reduce waiting. A pilot must test service benefits and any extra staff effort.
EVIDENCE AND QUALIFICATIONS
P1 的待验证价值链是：明确接收与升级，让等待案例有清楚责任；预期减少等待和追问，进而加快恢复、减少客户重复联系并释放一线时间。图中保留拒绝、逾期和未知结果。这个机制须经诊断和后续可比试点验证，不能说成已经实现的效果；timer 仍是符号占位。
SOURCES
SAP. (n.d.). Modeling with the editor. Managing Business Processes with SAP Signavio Solutions, Unit 4, Lesson 3.
https://learning.sap.com/courses/managing-business-processes-with-sap-signavio-solutions/the-editor-quick-n-easy-modeling_fd121490-31f9-4229-a10a-8a3a68972fa3
SAP. (n.d.). Performing simulations. Managing Business Processes with SAP Signavio Solutions, Unit 4, Lesson 7.
https://learning.sap.com/courses/managing-business-processes-with-sap-signavio-solutions/basic-simulation_fbe67690-eb99-4861-9773-2b05c0144e79

## Slide 10: SAP capabilities support specific decisions
Tools follow a validated need
Learning Journey | Application in this proposal
Signavio | AS-IS / TO-BE review; later validated simulation
LeanIX | Application and partner dependency inventory
Analytics Cloud | Comparable KPI views, including missing outcomes
Build | Conditional referral forms and authorised actions
Cloud ALM | Project owners, gates, tests and defects
Signavio models exist. Other uses are proposed and depend on Spark’s technology and justified scope.
SAP Learning (n.d.). Five courses and eight lessons, listed on slide 19.
Check existing tools, authorised access and full implementation costs.
Notes: SPOKEN SCRIPT — 10 — 20 seconds
I have prepared Signavio models. The other tools could support dependencies, measurement, forms and testing, subject to Spark’s systems, access and a justified need.
EVIDENCE AND QUALIFICATIONS
The Signavio AS-IS and conditional P1 models exist. The other applications remain proposals, not evidence of deployed Spark systems. SAP Learning provides capability descriptions. A production choice requires authorised access, a confirmed technology fit and justified cost; a manual or existing-tool option remains valid.
覆盖 A2-D1 第 14 章，但不暗示 Spark 已采用全部 SAP 产品。已经完成的是 Signavio 流程图；其余是基于学习内容提出的条件性应用，现有工具或人工方案仍可更合适。
SOURCES
SAP. (n.d.). Modeling with the editor. Managing Business Processes with SAP Signavio Solutions, Unit 4, Lesson 3.
https://learning.sap.com/courses/managing-business-processes-with-sap-signavio-solutions/the-editor-quick-n-easy-modeling_fd121490-31f9-4229-a10a-8a3a68972fa3
SAP. (n.d.). Performing simulations. Managing Business Processes with SAP Signavio Solutions, Unit 4, Lesson 7.
https://learning.sap.com/courses/managing-business-processes-with-sap-signavio-solutions/basic-simulation_fbe67690-eb99-4861-9773-2b05c0144e79
SAP. (n.d.). Defining SAP LeanIX fact sheets and modeling relations and dependencies. Learning to Use SAP LeanIX for Successful Enterprise Architecture, Unit 2, Lesson 2.
https://learning.sap.com/courses/learning-to-use-sap-leanix-for-successful-enterprise-architecture/defining-sap-leanix-fact-sheets-and-modeling-relations-and-dependencies_ce548272-cbab-4d1d-b94b-77d5c13c3935
SAP. (n.d.). Configuring charts. Designing Stories in SAP Analytics Cloud, Unit 3, Lesson 2.
https://learning.sap.com/courses/designing-stories-in-sap-analytics-cloud/configuring-charts_ca6acc40-01e5-4f3b-8d7f-1ce8747a628c
SAP. (n.d.). Digitalizing user interactions with forms. Developing with SAP Build Process Automation, Unit 3, Lesson 3.
https://learning.sap.com/courses/developing-with-sap-build-process-automation/digitalizing-user-interactions-with-forms_d0e78947-8cff-45f0-9b85-d82c1ed0394e
SAP. (n.d.). Encapsulating the APIs of remote systems using actions projects. Developing with SAP Build Process Automation, Unit 5, Lesson 2.
https://learning.sap.com/courses/developing-with-sap-build-process-automation/encapsulating-the-apis-of-remote-systems-using-actions-projects_d102638b-94d7-4c2e-9547-bb344e9aa9de
SAP. (n.d.). Setting-up the project and teams. Implementing with SAP Cloud ALM, Unit 2, Lesson 1.
https://learning.sap.com/courses/implementing-with-sap-cloud-alm/setting-up-the-project-and-teams_eee6ae76-7b22-4393-844d-be56ec4fe45a
SAP. (n.d.). Planning and executing testing. Implementing with SAP Cloud ALM, Unit 7, Lesson 1.
https://learning.sap.com/courses/implementing-with-sap-cloud-alm/planning-and-executing-testing_ef46a49b-9885-4aaa-841d-5ac9c80a3681

## Slide 11: Delivery phases and approval decisions
1–6
7–10
11–18
19–22
23–24
24 delivery weeks across 27 calendar weeks
Diagnosis
G1
Design
G2
Pilot
G3
Evaluation
G4
Handover
G5
Delivery weeks
Proposed: 28 Sep 2026–4 Apr 2027. Pause new enrolment 21 Dec–10 Jan; follow enrolled cases throughout.
G1: supported option and affordable design, or stop.
Notes: SPOKEN SCRIPT — 11 — 20 seconds
The full plan spans twenty-four delivery weeks, with approvals between phases. During the proposed year-end pause, customer service continues and already enrolled cases remain under observation.
EVIDENCE AND QUALIFICATIONS
五个阶段分别是诊断、设计、试点、评价、移交。24 个交付周加 3 周暂停，共 27 个日历周；暂停的是新实验入组和常规项目交付，不是客户故障服务或已入组案例跟进。
SOURCES
Author proposal, planning assumption or reconstructed process. Not an observed Spark result.

## Slide 12: A proposed team with clear accountability
Hypothetical consulting profiles
Role | Accountable output
Ryan Li Engagement and operational lead | Evidence, process design and funding gates
Rae Huang Financial lead | Cost reconciliation and realised savings
Francis Lee Strategic lead | Option appraisal and investment challenge
Xuan Zeng Organisational lead | Readiness, adoption and ownership transfer
Assumed project capabilities, not claims of professional experience or Spark employment.
Client decision rights
Spark owns production changes, partner commitments and service decisions.
Notes: SPOKEN SCRIPT — 12 — 20 seconds
I lead operations, with financial, strategic and organisational support from the team. These are proposed consulting roles. Spark keeps authority over live changes and service decisions.
EVIDENCE AND QUALIFICATIONS
沿用提案团队角色，明确 hypothetical，不编造真实咨询履历或 Spark 任职。角色覆盖完整 business case 并不表示需要汇总四位组员各自的 A2-D1 题目。
SOURCES
Author proposal, planning assumption or reconstructed process. Not an observed Spark result.

## Slide 13: Client resources needed for diagnosis
Sponsor and service owner
540 client hours
Conditional full engagement
NZ$43,200 opportunity cost
At an assumed NZ$80/hour
160 client hours in the initial six weeks
Diagnosis time: NZ$12,800 opportunity cost at NZ$80/hour. Separate from consultant cash fees.
Mills, 2025, 37:13–50:34; 1:00:36–1:06:53
Confirm scope, owners and decision access.
Approved data and frontline access
Provide deidentified records and staff walkthroughs.
Partner liaison and Finance review
Agree handoff rules and check the revised costs.
The initial 160 hours are included in the full 540-hour allowance.
Notes: SPOKEN SCRIPT — 13 — 20 seconds
Diagnosis needs one hundred and sixty client hours, plus agreed owners and access. Staff time has an opportunity cost, separate from the consulting cash commitment.
EVIDENCE AND QUALIFICATIONS
The initial diagnosis requires 160 client hours (A2-D1 D1–D4) alongside 208 consultant hours. At an assumed NZ$80/hour, diagnostic client opportunity cost is NZ$12,800. The conditional full engagement assumes 540 client hours, or NZ$43,200 at that same rate; the 160 diagnostic hours are included in, not additional to, the 540. Neither opportunity cost is added as a second cash outflow. Agree access, decision owners and workshop participation at initiation.
当前诊断审批同时需要 160 客户小时，按 $80/h 的规划单价计 $12,800 机会成本；它不属于咨询现金费用。完整项目 540 小时／$43,200 包含这 160 小时，不能再次叠加。客户须提供赞助人、服务负责人、数据与一线人员访问、合作方联络及财务核对。
SOURCES
Mills, A. (2025, August 26). Guest lecture Andrew Mills INFOSYS 704 [Video]. University of Auckland.
https://auckland.au.panopto.com/Panopto/Pages/Viewer.aspx?id=b95c7f4e-914b-486b-bc74-b4b200627d8a

## Slide 14: Readiness before live use
Practise normal and exception cases
Daily reviews for the first
two live delivery weeks
Then weekly reviews,
if service remains stable
A bounded pilot with a recovery path
At handover: transfer the operating guide, exception queue,
training and monthly benefits review to Spark.
Mills, 2025, 37:13–50:34; 1:00:36–1:06:53
Normal, overdue, rejected and reopened referrals
Confirm partner responsibilities
Named contacts, acceptance and escalation rules
Test rollback before launch
G2 requires service, security and partner readiness
Notes: SPOKEN SCRIPT — 14 — 20 seconds
Before launch, staff practise exceptions, confirm partner responsibilities and test rollback. Early reviews check service and workload. At handover, Spark takes ownership of the operating guide.
EVIDENCE AND QUALIFICATIONS
实施采用有限试点与独立扩展审批。确保所有试点员工通过实操检查，严重服务或隐私事件暂停变更并恢复原程序，移交时客户必须能独立处理异常。
SOURCES
Mills, A. (2025, August 26). Guest lecture Andrew Mills INFOSYS 704 [Video]. University of Auckland.
https://auckland.au.panopto.com/Panopto/Pages/Viewer.aspx?id=b95c7f4e-914b-486b-bc74-b4b200627d8a

## Slide 15: Risk owners and response triggers
Controls protect service and the value of the change
Risk | Accountability and response
Wrong cause or weak records | Ryan + analyst: evidence or repair at G1
Partner responsibility unclear | Partner liaison: agreement before G2
Added administration | Xuan + team leader: measure net handling time
Service or privacy incident | Service / security leads: pause affected change
Insufficient value | Rae + sponsor: narrow scope or stop
Initial planning judgements. Review red risks weekly and at gates; ratings improve only with evidence.
Scott & Vessey, 2002, pp. 75–77
Before funding: recheck case volumes, net time saved and cash conversion.
Notes: SPOKEN SCRIPT — 15 — 20 seconds
Each risk has an owner and a response. Measure total handling time, because extra administration could erase savings. Serious service or privacy incidents suspend the affected change.
EVIDENCE AND QUALIFICATIONS
R1 wrong cause: Ryan, with no G1 approval without supporting episode evidence. R2 incomplete records: client analyst and Ryan; below 90% reconstruction, repair measurement or narrow scope. R3 partner access/accountability: client partner liaison; agree responsibilities and minimum access before G2, otherwise narrow to an authorised option or stop. R4 administrative burden/workarounds: Xuan and client team leader; measure total handling time and simplify when work shifts rather than falls. R5 service interruption/incorrect messages: client service owner; sandbox tests, limited rollout and rollback drill, with affected change suspended after a serious incident. R6 data exposure: client security lead; minimise fields, approve access and retention, reject unapproved transfers before G2. R7 insufficient value: Rae and sponsor; revalidate volumes, net minutes and cash conversion, then narrow or stop if value is insufficient. R8 seasonal/partner delay: Ryan and partner liaison; confirm pause and comparable observation windows, rebaseline without hiding lost sample coverage. Review red risks weekly and before each gate. These are planning judgements, not measured probabilities.
为风险补上负责人及触发后的行动。新增行政负担由 Xuan 与客户 team leader 检查，必须测量总处理时间，才能支持财务模型的净节省分钟数。服务负责人处理恢复与暂停变更，安全负责人拒绝未经批准的数据转移；Rae 与赞助人重新检查价值。不是所有风险都自动停止，有的触发测量修复、简化或重新排期；完整八项见英文备查。
SOURCES
Scott, J. E., & Vessey, I. (2002). Managing risks in enterprise systems implementations. Communications of the ACM, 45(4), 74–81.
https://doi.org/10.1145/505248.505249

## Slide 16: The base case does not justify full investment
Assumed annual net cash after recurring operating costs
Chart: 
| Downside | Base | Upside
Annual net cash (NZD) | -12000 | -1750 | 96000
Input | Downside | Base | Upside
Episodes / year | 6,000 | 12,000 | 24,000
Net minutes / case | 2 | 5 | 8
Cost / hour | NZ$55 | NZ$65 | NZ$75
Cash realisation | 0% | 25% | 50%
Annual Opex | NZ$12,000 | NZ$18,000 | NZ$24,000
Base: NZ$16,250 cash savings − NZ$18,000 Opex = −NZ$1,750/year
Three-year base net cash: −NZ$159,258
Upside payback: 1.60 years after handover
Author assumptions for annual operation after handover. A small regional pilot cannot establish these volumes.
Notes: SPOKEN SCRIPT — 16 — 20 seconds
The base scenario has a cash shortfall. Only the upside pays back, under stronger assumptions. These estimates support further investigation, not approval of the full investment.
EVIDENCE AND QUALIFICATIONS
All scenarios are author assumptions for annual operation after handover, not Spark forecasts. Annual net cash = eligible episodes × net minutes saved ÷ 60 × hourly cost × cash realisation − recurring Opex. Downside: 6,000 episodes, 2 minutes, NZ$55/hour, 0% cash realisation and NZ$12,000 Opex = −NZ$12,000. Base: 12,000 episodes, 5 minutes, NZ$65/hour, 25% and NZ$18,000 Opex = −NZ$1,750. Upside: 24,000 episodes, 8 minutes, NZ$75/hour, 50% and NZ$24,000 Opex = +NZ$96,000. A small regional pilot cannot establish these annual footprints. Finance must validate eligible volume, net handling time after added administration, and whether released capacity genuinely becomes cash. Base capacity is 1,000 hours worth NZ$65,000; NZ$16,250 cash realisation is a subset, not an additional benefit. Three-year net cash subtracts the full NZ$154,008 ceiling once: downside −NZ$190,008; base −NZ$159,258; upside +NZ$133,992. Undiscounted, with no inflation or ramp-up. Only the upside pays back, at 154,008 / 96,000 = 1.60 years after handover. Incremental steady-state EBITDA equals annual net cash only under the expense/cash timing assumptions. Base three-year net cash remains negative under 0%, 5% and 10% annual episode-volume growth (−159,258; −156,780; −154,221). Higher fault volume is workload growth, not revenue growth. The value of diagnostic information has not been monetised, and uncommitted later-phase funding is not an achieved saving.
三个情景全部是移交后的年度运营假设。下行：6,000 案例、2 分钟、$55/h、0% 现金实现、$12,000 Opex，净现金 −$12,000；基础：12,000、5、$65、25%、$18,000，净现金 −$1,750；上行：24,000、8、$75、50%、$24,000，净现金 +$96,000。小型区域试点不能证明这些年度规模。基础节省 1,000 小时，$65,000 capacity 中只有 $16,250 假设转成现金，不能把两者加总。三年基础净现金 −$159,258；上行才有 1.60 年移交后回本，均未折现且未计爬坡。
SOURCES
Author proposal, planning assumption or reconstructed process. Not an observed Spark result.

## Slide 17: The diagnosis approval request
Six-week diagnosis ceiling
208 consultant hours + 160 client hours
NZD excluding GST
NZ$154,008
Conditional full-engagement ceiling
NZ$117,162
Remains uncommitted
NZ$36,846
NZ$31,040 fees + $1,000 allowance + $4,806 reserve
Monthly billing for approved hours and expenses, payable in 30 days.
Time and materials within phase caps; unused reserve is not billed.
Mills, 2025, 37:13–50:34; 1:00:36–1:06:53; Prodigi Technology Services, n.d.
Notes: SPOKEN SCRIPT — 17 — 20 seconds
The diagnosis ceiling is thirty-six thousand, eight hundred and forty-six dollars, excluding GST. Later phases need separate approval. Unused reserve is not billed.
EVIDENCE AND QUALIFICATIONS
Diagnosis fees: 96 engagement-manager hours × NZ$160 plus 112 other consultant hours × NZ$140 = NZ$31,040. Add NZ$1,000 allowance and 15% reserve (NZ$4,806) for NZ$36,846. Full engagement: NZ$121,920 fees + NZ$12,000 allowance + NZ$20,088 reserve = NZ$154,008. Treat cash provisionally as Opex; planned Capex is zero, subject to Finance review for any later development. National rollout and major integrations require a separate scope.
审批请求包含 NZ$36,846 现金上限和 160 客户小时。诊断咨询投入为 208 小时：$31,040 fees + $1,000 allowance + $4,806 reserve。完整条件上限 $154,008；余款 $117,162 尚未承诺，不能称为已实现节约。后续阶段按证据重估，月度按获批实际工作计费，未用 reserve 不收取。
SOURCES
Mills, A. (2025, August 26). Guest lecture Andrew Mills INFOSYS 704 [Video]. University of Auckland.
https://auckland.au.panopto.com/Panopto/Pages/Viewer.aspx?id=b95c7f4e-914b-486b-bc74-b4b200627d8a
Prodigi Technology Services Limited. (n.d.). All our pricing, no meetings required. Retrieved September 15, 2026.
https://prodigi.nz/pricing

## Slide 18: Sources for the business case
Original published sources and teaching material
Commerce Commission (2026a)
Consumer satisfaction metrics: Methodology & guide – June 2026
comcom.govt.nz
Commerce Commission (2026b)
Customer service and billing rankings – June 2026
comcom.govt.nz
Spark New Zealand (2026a)
Spark annual report FY26
investors.sparknz.co.nz
Spark New Zealand (2026b)
Spark New Zealand FY26 results summary
investors.sparknz.co.nz
Rosenbaum, Otalora & Ramírez (2017)
How to create a realistic customer journey map
doi.org/10.1016/j.bushor.2016.09.010
Mills (2025, 26 August)
Guest lecture Andrew Mills INFOSYS 704
University of Auckland, Panopto
Scott & Vessey (2002)
Managing risks in enterprise systems implementations
doi.org/10.1145/505248.505249
Prodigi Technology Services (n.d.)
All our pricing, no meetings required
prodigi.nz/pricing (accessed 15 Sep 2026)
Published facts inform the context. Targets and costs are assumptions.
Diagnostic information value is not monetised; the sponsor must judge its worth.
Notes: SPOKEN SCRIPT — 18 — 20 seconds
Public reports support the context; research informs the method. Targets and costs remain assumptions. The sponsor must judge whether the diagnostic outputs justify their cost.
EVIDENCE AND QUALIFICATIONS
画面逐项显示八项来源的作者、年份、题名及定位信息，明确 2026a/b 对应，补回 Rosenbaum 方法来源。完整链接还保留在英文讲稿和 PPT 备注。口述借此回到当前审批判断：诊断信息价值尚未货币化，赞助人应先判断这些具体产出是否值得其成本。自己的未发表 A1/A2-D1 不列作外部参考文献。
SOURCES
Commerce Commission. (2026a, August 18). Consumer satisfaction metrics: Methodology & guide – June 2026.
https://www.comcom.govt.nz/assets/Uploads/Consumer-Satisfaction-Metrics-Methodology-Guide-June-2026.pdf
Commerce Commission. (2026b). Customer service and billing rankings – June 2026.
https://www.comcom.govt.nz/assets/Uploads/Customer-Service-and-Billing-Rankings-June-2026.pdf
Spark New Zealand Limited. (2026a, August 20). Spark annual report FY26.
https://investors.sparknz.co.nz/FormBuilder/_Resource/_module/gXbeer80tkeL4nEaF-kwFA/doc/FY26_Annual_Report.pdf
Spark New Zealand Limited. (2026b). Spark New Zealand FY26 results summary.
https://investors.sparknz.co.nz/FormBuilder/_Resource/_module/gXbeer80tkeL4nEaF-kwFA/doc/H2FY26_Results_Presentation.pdf
Rosenbaum, M. S., Otalora, M. L., & Ramírez, G. C. (2017). How to create a realistic customer journey map. Business Horizons, 60(1), 143–150.
https://doi.org/10.1016/j.bushor.2016.09.010
Mills, A. (2025, August 26). Guest lecture Andrew Mills INFOSYS 704 [Video]. University of Auckland.
https://auckland.au.panopto.com/Panopto/Pages/Viewer.aspx?id=b95c7f4e-914b-486b-bc74-b4b200627d8a
Scott, J. E., & Vessey, I. (2002). Managing risks in enterprise systems implementations. Communications of the ACM, 45(4), 74–81.
https://doi.org/10.1145/505248.505249
Prodigi Technology Services Limited. (n.d.). All our pricing, no meetings required. Retrieved September 15, 2026.
https://prodigi.nz/pricing

## Slide 19: Sources for the proposed SAP applications
SAP Learning (n.d.) at learning.sap.com/courses
Managing Business Processes with SAP Signavio Solutions
U4 L3 Modeling with the editor
U4 L7 Performing simulations
Learning to Use SAP LeanIX for Successful Enterprise Architecture
U2 L2 Defining SAP LeanIX fact sheets and modeling relations and dependencies
Designing Stories in SAP Analytics Cloud
U3 L2 Configuring charts
Developing with SAP Build Process Automation
U3 L3 Digitalizing user interactions with forms
U5 L2 Encapsulating the APIs of remote systems using actions projects
Implementing with SAP Cloud ALM
U2 L1 Setting-up the project and teams
U7 L1 Planning and executing testing
Official capability descriptions. Adoption requires a justified need and a fit with Spark’s existing systems.
Notes: SPOKEN SCRIPT — 19 — 20 seconds
These SAP courses explain the proposed capabilities. They do not establish Spark’s current systems or licence costs. We would first check whether existing tools are sufficient.
EVIDENCE AND QUALIFICATIONS
画面显示五个完整课程名称、八个课次及各自标题，按 SAP Learning 课程与单元可定位原文，完整链接列在英文讲稿。课程支持工具能力，不代表 Spark 已部署这些产品。口述强调可以选择更小的现有工具改动，并在 G1 用修订范围和价格决定后续投入。
SOURCES
SAP. (n.d.). Modeling with the editor. Managing Business Processes with SAP Signavio Solutions, Unit 4, Lesson 3.
https://learning.sap.com/courses/managing-business-processes-with-sap-signavio-solutions/the-editor-quick-n-easy-modeling_fd121490-31f9-4229-a10a-8a3a68972fa3
SAP. (n.d.). Performing simulations. Managing Business Processes with SAP Signavio Solutions, Unit 4, Lesson 7.
https://learning.sap.com/courses/managing-business-processes-with-sap-signavio-solutions/basic-simulation_fbe67690-eb99-4861-9773-2b05c0144e79
SAP. (n.d.). Defining SAP LeanIX fact sheets and modeling relations and dependencies. Learning to Use SAP LeanIX for Successful Enterprise Architecture, Unit 2, Lesson 2.
https://learning.sap.com/courses/learning-to-use-sap-leanix-for-successful-enterprise-architecture/defining-sap-leanix-fact-sheets-and-modeling-relations-and-dependencies_ce548272-cbab-4d1d-b94b-77d5c13c3935
SAP. (n.d.). Configuring charts. Designing Stories in SAP Analytics Cloud, Unit 3, Lesson 2.
https://learning.sap.com/courses/designing-stories-in-sap-analytics-cloud/configuring-charts_ca6acc40-01e5-4f3b-8d7f-1ce8747a628c
SAP. (n.d.). Digitalizing user interactions with forms. Developing with SAP Build Process Automation, Unit 3, Lesson 3.
https://learning.sap.com/courses/developing-with-sap-build-process-automation/digitalizing-user-interactions-with-forms_d0e78947-8cff-45f0-9b85-d82c1ed0394e
SAP. (n.d.). Encapsulating the APIs of remote systems using actions projects. Developing with SAP Build Process Automation, Unit 5, Lesson 2.
https://learning.sap.com/courses/developing-with-sap-build-process-automation/encapsulating-the-apis-of-remote-systems-using-actions-projects_d102638b-94d7-4c2e-9547-bb344e9aa9de
SAP. (n.d.). Setting-up the project and teams. Implementing with SAP Cloud ALM, Unit 2, Lesson 1.
https://learning.sap.com/courses/implementing-with-sap-cloud-alm/setting-up-the-project-and-teams_eee6ae76-7b22-4393-844d-be56ec4fe45a
SAP. (n.d.). Planning and executing testing. Implementing with SAP Cloud ALM, Unit 7, Lesson 1.
https://learning.sap.com/courses/implementing-with-sap-cloud-alm/planning-and-executing-testing_ef46a49b-9885-4aaa-841d-5ac9c80a3681

## Slide 20: Decision requested Six-week diagnosis
160 client hours, with agreed owners and access.
Proposed kickoff: 28 September 2026.
Week six: revised scope and price, or stop.
NZ$36,846 excluding GST
Proposed dates and commercial terms require client agreement.
Notes: SPOKEN SCRIPT — 20 — 20 seconds
I recommend approving the six-week diagnosis, with client owners, time and data access agreed. At week six, Spark can proceed, change scope or stop. Thank you.
EVIDENCE AND QUALIFICATIONS
最后请求批准诊断现金上限及 160 客户小时，前提是负责人、合作方参与和数据访问得到同意。9 月 28 日是拟议启动日，并非既定客户承诺。第六周交付证据、修订范围与价格，客户可以停止；本次不批准整项 $154,008 投资。
SOURCES
Author proposal, planning assumption or reconstructed process. Not an observed Spark result.