## Slide 1
BUSINESS CASE | SPARK NEW ZEALAND
When people leave,
keep what they know
A gated knowledge handover for knowledge-critical role exits
Presented to the Chief Executive Officer
Xuan Zeng | INFOSYS 704 | A2-D2 | September 2026
Departing
employee
Receiving
owner
verified gate
Notes: [1/20 | 20 seconds | 40 words] Good morning. I'm Xuan Zeng. Spark has cut costs, and those savings matter. Today I will show you how to protect them. My idea is simple: when people in key roles leave, we make sure their knowledge stays with Spark.

## Slide 2
EXECUTIVE SUMMARY
02 / 20
The decision: approve a four-week validation phase
NZ$22,500
Phase 0 validation
4 weeks, low-risk first step
52 weeks
Phased trial
validate, pilot, extend, embed
NZ$1.4m
Target annual recovery
from rework and contractors
Full fee NZ$97,350
Three-year net benefit NZ$3.34m | Benefit-cost ratio 22.2
Proposed kick-off: within one week of approval
Source: A2-D1 Consulting Proposal, Sections 1, 10 and 12. Figures are working estimates to be validated in Phase 0.
Notes: [2/20 | 20 seconds | 46 words] Here is my request. I suggest a fifty-two-week trial, done in small steps. It starts with a four-week check that costs twenty-two thousand five hundred dollars. The full fee is about ninety-seven thousand dollars. The goal is to save one point four million dollars a year.

## Slide 3
CLIENT CONTEXT AND URGENCY
03 / 20
Spark is cutting cost while its structure changes
3,847
FTE employees at 30 June 2025
~1,300
full-time roles reduced
NZ$50m
labour cost reduction plan
63%
Spark mobile satisfaction, near the bottom of providers
July 2026
Connectivity separated from Digital Services. SPK 30 depends on network quality and customer experience, and more roles will change.
Sources: Spark New Zealand (2025a, 2025b, 2026); Pelletier (2024); Harvey (2025); Bennett (2026).
Notes: [3/20 | 20 seconds | 47 words] Spark is New Zealand's biggest telco. Its SPK 30 plan needs a strong network and happy customers. Spark has cut about thirteen hundred jobs to save fifty million dollars. In July, it also split into two parts. More change is coming, so now is the right time.

## Slide 4
PROBLEM STATEMENT
04 / 20
The exit process controls everything except knowledge
Payroll finalised
Assets returned
System access revoked
Knowledge reached the receiver
1
No evidence standard
Nothing defines what a complete handover is
2
No receiver sign-off
The person taking over never confirms
3
No completion measure
Nobody can see if it worked
Result: rework, slower fault resolution and unplanned contractor spend that erode the savings from the cost programme.
Notes: [4/20 | 20 seconds | 45 words] Here is the problem. When people leave, Spark checks pay, laptops and system access. But no one checks if their knowledge has passed to the next person. There is no standard, no sign-off and no measure. So problems only show up after people have gone.

## Slide 5
CURRENT (AS-IS) PROCESS
05 / 20
Today, the gap appears after the employee has left
Manager confirms exit
No criticality check (CAC not measured)
Employee prepares handover
Own discretion, no template (VHCR not measured)
People admin checklist
Covers admin, not readiness
Access revoked on final day
Notice period can expire first (HVLT not measured)
Receiving team finds gaps
Rework, escalation, premium contractors
The administrative process ends when access is revoked.
Knowledge rebuilding starts after that point and nobody controls it.
Simplified from Figure 1, AS-IS BPMN model (A2-D1).
Notes: [5/20 | 20 seconds | 46 words] This is how it works today. The manager confirms the exit. The employee writes a handover in their own way. HR finishes a checklist, and access is closed. Only then does the new team find what is missing. This leads to rework, delays and costly contractors.

## Slide 6
COST OF INACTION
06 / 20
The hidden cost: up to NZ$4.0m every year
Chart: Estimated annual capability leakage (NZ$m)
| Low case | Base case | High case
Annual leakage (NZ$m) | 1.1 | 2.4 | 4
Current baseline
Verified handover completion
Below 50% (estimate)
Criticality assessment coverage
Not measured
Verification lead time
Not measured
Source: A1-D2 sensitivity analysis, restated in A2-D1 Table 1 and Section 10.1.
Notes: [6/20 | 20 seconds | 47 words] So what does this cost? Less than half of handovers are checked by the person taking over. Other steps are not measured at all. We think this hidden cost is one point one to four million dollars a year. Our middle estimate is two point four million.

## Slide 7
OBJECTIVES
07 / 20
Four objectives protect capability and keep cost discipline
Verify
A provable completion condition for every knowledge-critical exit
Detect
Identify critical roles within five working days of exit confirmation
Reduce
Cut post-exit rework, escalation and unplanned recovery cost
Repeat
A reusable control for internal transfers and role redesigns
12-month target At least 90% verified handovers and a supported route to NZ$1.4m annual savings, against a validated FY26 baseline.
Notes: [7/20 | 20 seconds | 42 words] The plan has four goals. First, make every key handover provable. Second, find key roles within five working days. Third, cut rework and extra contractor costs. And fourth, build a process Spark can reuse later, for job moves and role changes too.

## Slide 8
SUCCESS CRITERIA
08 / 20
Success is measured, not assumed
Chart: Verified Handover Completion Rate (VHCR)
| Baseline | Week 20 | Week 32 | Week 52
VHCR target | 50 | 60 | 75 | 90
Baseline is an estimate (below 50%)
CAC
Criticality assessment coverage
100% by week 32
HVLT
Verification lead time
5+ days before last day
Cost
Capability recovery cost
NZ$1.4m run-rate cut
Reopen
90-day knowledge escalations
25% reduction
Notes: [8/20 | 20 seconds | 45 words] We will measure success with clear numbers. Checked handovers will grow to sixty, then seventy-five, then ninety percent by week fifty-two. Every exit will get a risk check. Checks will finish five days before the last day. And repeat problems will drop by a quarter.

## Slide 9
PROPOSED APPROACH
09 / 20
Hypothesis: knowledge is lost because nothing requires it
If the receiving owner must confirm completion, handover quality improves and recovery costs fall.
Observed failure | Proposed control | Evidence generated
No criticality test | Rules-based triage (role, access, tenure, systems) | CAC and overrides
No accountable receiver | Named receiving owner at exit confirmation | Owner and exception log
Unstructured capture | Standard pack driven by receiver needs | Comparable artefact
No quality gate | Competence check on 2 to 3 real tasks | VHCR and remediation
Costs stay invisible | Link exit, ITSM and finance records | Benefit tracking
Links A1-D1 and A1-D2 findings to controls; process models kept understandable to business owners (Rosemann, 2006).
Notes: [9/20 | 20 seconds | 47 words] Our idea is simple. We believe knowledge is lost because no one has to prove it was passed on. So for each problem, we add one control and one piece of proof. For example, if there is no clear receiver, we name one person to take over.

## Slide 10
FUTURE (TO-BE) PROCESS
10 / 20
Tomorrow, a gate proves the receiver can do the work
1
Criticality triage
2
Named receiving owner
3
Standard handover pack
4
Competence check on real tasks
5
Managed exception route
6
Monthly KPI reporting
Competence check passed?
Yes Verified, backfill approved
No Remediate or named exception
Security is never delayed: access is revoked on schedule, and the receiving owner gets time-limited, read-only access to records.
Notes: [10/20 | 20 seconds | 44 words] This is the new process. It adds six steps: a risk check, a named receiver, a standard handover pack, a test on real tasks, a clear exception route, and a monthly report. Security is never delayed. Access is still closed on the last day.

## Slide 11
PROPOSED METHODOLOGY
11 / 20
Five stages, each with a decision gate
Validate
Confirm the gap and baseline
Gate: Gap proven with data
Configure
Build workflow, rules and forms
Gate: Security, Privacy, People and Finance review
Pilot
Test in Connectivity
Gate: VHCR 60%+, no high-risk defect
Extend
Digital Services and transfers
Gate: VHCR 75%+, owners accept
Embed
Normal management and tracking
Gate: VHCR 90%+, BAU acceptance
SAP Learning Journeys that strengthen delivery
Signavio
model and analyse
LeanIX
map dependencies
Analytics Cloud
KPIs and value
Build
prototype workflow
Cloud ALM
tests and gates
Lifecycle logic: Markus and Tanis (2000); phase deliverables and sign-off: Mills (2025).
Notes: [11/20 | 20 seconds | 42 words] We will deliver this in five stages: validate, configure, pilot, extend and embed. Each stage ends with a clear decision, so Spark only moves on when the results are good. SAP tools like Signavio, LeanIX and Analytics Cloud can support this work.

## Slide 12
WORK PLAN AND TIMELINE
12 / 20
A 52-week plan with five decision milestones
0 Validate baseline
W1-4
1 Configure workflow
W5-8
2 Pilot in Connectivity
W9-20
3 Extend to Digital Services
W21-32
4 Embed and track benefits
W33-52
W1
W4
W8
W20
W32
W52
W4
Baseline approved
W8
Configuration signed off
W20
Pilot go / no-go
W32
Division rollout accepted
W52
Handover to BAU
Timings are assumptions; the steering committee resets the schedule at the week 4 gate if volumes or capacity differ.
Notes: [12/20 | 20 seconds | 47 words] Here is the timeline. In weeks one to four, we check the data. In weeks five to eight, we set up the process. Then we test it in Connectivity, extend it to Digital Services, and make it part of daily work. There are five key decision points.

## Slide 13
TEAM AND CAPABILITIES
13 / 20
A small joint team with clear ownership
Xuan Zeng
Project lead
Completed the A1-D1 diagnosis and A1-D2 analysis, including BPMN models and cost estimates. Leads analysis, process design and phase gates.
Executive Sponsor
Cross-divisional authority, links to SPK 30
Process Owner
People Services, owns the standard
Finance Benefits Lead
Validates baseline and benefits
HRIS and Workflow Analyst
Configures fields and dashboards
Security and Privacy Adviser
Protects offboarding and data
Divisional Change Leads
Connectivity and Digital Services
Spark roles are nomination profiles, to be named before Phase 0 starts.
Notes: [13/20 | 20 seconds | 45 words] The team is small, because we are improving a process, not buying new software. I will lead the analysis, the design and the reviews. Spark will name a sponsor, a process owner, a finance lead, a systems analyst, a security adviser and two change leads.

## Slide 14
CHANGE MANAGEMENT
14 / 20
Phased change: learn in Connectivity, then extend
Big bang
All risk in one go-live
Parallel
Overlapping work overloads staff
Phased
Smaller go-lives; lessons carry forward
Who changes
Managers: classify and assign owners
Leavers: complete pack, shadow tasks
Receivers: define needs, run checks
People and Finance: new control
1
Sponsor briefing
2
Role training
3
Pilot office hours
4
T+45 feedback
5
Monthly KPIs
Implementation strategies: INFOSYS 704 (2026) Week 5 Lecture 7; Mills (2025).
Notes: [14/20 | 20 seconds | 45 words] For change, I suggest a step-by-step approach. Changing everything at once is too risky. Running many parts at the same time would overload staff. So we start with Connectivity and learn first. Staff get training time, weekly support, and a feedback check after forty-five days.

## Slide 15
RISK MANAGEMENT
15 / 20
Nine risks tracked; one red risk actively controlled
1
Red
7
Amber
1
Green
R2
Exception path becomes the default
Name approvers, block backfill, report to sponsor
R1
Receivers sign without testing
Real tasks, 10% quarterly assurance sample
R3
Critical roles under-classified
Use access and on-call data; bias upward
R7
Benefits overstated
Separate planned from unplanned spend
R6
Pack holds credentials or personal data
Prohibit credentials; retention rules
Why R2 is red: cost pressure creates a strong incentive to bypass the gate, so every override is visible to the executive sponsor.
Risk types and interaction: Scott and Vessey (2002); scope control: Mills (2025). RAG shows residual exposure after mitigation.
Notes: [15/20 | 20 seconds | 46 words] Using the Scott and Vessey model, we found nine risks. Only one is red: people may skip the test and use exceptions instead. To stop this, every exception needs a named approver and is reported to the sponsor. Seven risks are amber, and one is green.

## Slide 16
EXPECTED IMPACT: FINANCIAL
16 / 20
NZ$3.5m benefit for NZ$157k over three years
Chart: Benefit vs cost (NZ$ thousands)
| Year 1 | Year 2 | Year 3
Recovered cost | 700 | 1400 | 1400
Fee and assurance | 97.35 | 30 | 30
NZ$3.34m
three-year net benefit
22.2
benefit-cost ratio
+NZ$1.4m
annual EBITDAI uplift once validated; no revenue assumed
Source: A2-D1 Table 9. Year 1 at 50% benefit ramp; indicative until validated in Phase 0.
Notes: [16/20 | 20 seconds | 42 words] Now the value. Even if we count only half the savings in year one, three-year savings reach three point five million dollars. The total cost is only one hundred and fifty-seven thousand dollars. So every dollar spent brings back about twenty-two dollars.

## Slide 17
EXPECTED IMPACT: VALUE
17 / 20
Start where value and feasibility are highest
Do first
1
2
3
4
5
6
1
2
3
4
5
3
4
5
Implementation feasibility
Value
1 Verified handover gate 2 Criticality triage
3 Named receiving owner 4 Standard handover pack
5 T+45 review 6 Deputy register (phase two)
Strategic
Protects the network and customer capabilities SPK 30 needs
Operational
Less rework and escalation; faster independence
Organisational
Clear ownership; shows weak deputy cover
Governance
Links labour savings to hidden recovery cost
Notes: [17/20 | 20 seconds | 45 words] The value is not just money. It protects the network and customer service. It cuts rework. And it makes someone clearly responsible for knowledge. On this chart, the handover test, the risk check and the named receiver give the most value, so they come first.

## Slide 18
CLIENT RESPONSIBILITIES AND COLLABORATION
18 / 20
What we need from Spark
Before kick-off
Nominate executive sponsor and process owner
Week 1
Controlled access to HRIS, entitlement, ITSM and finance data
Weeks 1-8
SMEs from People, Finance, Security, IT and divisions
Weeks 8-20
Release pilot staff for training and competence checks
Ongoing
Attend forums and resolve escalations
Governance forums
Steering committee
Monthly, 60 min
Delivery stand-up
Weekly, 30 min
Pilot exception review
Weekly in pilot, 45 min
Benefits review
Quarterly, 60 min
Knowledge transfer test: by week 52 the process owner runs the dashboard, manages an exception and updates the standard without consultant support.
Notes: [18/20 | 20 seconds | 47 words] To make this work, we need Spark's help. Please name a sponsor and a process owner, give us safe access to data in week one, and give staff time for training. We will meet every month. By week fifty-two, Spark will run the process on its own.

## Slide 19
COMMERCIALS: FEES AND TERMS
19 / 20
Fixed fee by phase: NZ$97,350 excluding GST
Chart: Fee by phase (NZD, 59 consulting days)
| 0 Validate | Mobilise | 1 Configure | 2 Pilot | 3 Extend | 4 Embed | Contingency 10%
Fee | 22500 | 13500 | 18000 | 15000 | 10500 | 9000 | 8850
NZ$0
Capex: no new platform
100%
Opex: services and training
Invoice at each phase acceptance, 20 business days
Scope changes approved before work starts
Spark owns all workflow, templates and reports
Excludes new software licences, travel and major integration. Contingency used only with steering committee approval.
Notes: [19/20 | 20 seconds | 47 words] The fee is fixed for each stage. The total is ninety-seven thousand, three hundred and fifty dollars, plus GST, including a ten percent buffer. Spark does not need to buy new systems. Spark pays after each stage is accepted, and any extra work must be approved first.

## Slide 20
NEXT STEPS
20 / 20
Approve Phase 0 today
1
Confirm sponsor, process owner, Finance lead and divisional reps
2
Approve the Phase 0 data access and pseudonymisation protocol
3
Schedule the 90-minute kick-off workshop
4
Release HRIS, entitlement, ITSM and finance extracts
5
Week 4 gate: confirm baseline, pilot scope and authority to configure
The ask
NZ$22,500
Phase 0 validation
Kick-off within one
week of approval
Make Spark's savings last. Thank you.
Notes: [20/20 | 20 seconds | 38 words] So my request is simple. Please approve the four-week check, for twenty-two thousand five hundred dollars. We can start within one week of approval, and report back in week four. Let's make sure Spark's savings last. Thank you.